## Tasks in Gantt format
Task | Description | Duration (Working Days) | Predecessor(s)
1 | Initial team meeting / Task allocations | 2d | None
2 | Creation of Google Docs | 1d | 2
3 | Creation of Github Repo | 1d | 2
4 | Non-functional requirements | 5d | 3
5 | Functional requirements | 4d | 3
6 | Domain Requirements & Feasibility study | 5d | 5,6
7 | Risk Management | 4d | 5,6
8 | Test Plan | 4d | 8
9 | Understanding C# | 10d | 4
10 | Use Case | 4d | 8
11 | Flowchart | 6d | 8
12 | Class Diagram | 4d | 11, 12
14 | Graphics / Wireframes | 5d | 11, 12
15 | (Cycle 1) User Stories / Task Cards | 3d | 8
16 | (Cycle 1) Coding | 8d | 10, 13, 15
17 | (Cycle 1) Testing & Documentation | 3d | 9, 18
18 | (Cycle 2) User Stories / Task Cards | 2d | 17
19 | (Cycle 2) Coding | 4d | 13, 18
20 | (Cycle 2) Testing & Documentation | 1d | 9, 19
21 | (Cycle 3) User Stories / Task Cards | 2d | 20
22 | (Cycle 3) Coding | 5d | 13, 21
23 | (Cycle 3) Testing & Documentation | 2d | 9, 22
24 | (Cycle 4) User Stories / Task Cards | 2d | 24
25 | (Cycle 4) Coding | 5d | 13, 14, 24
26 | (Cycle 4) Testing & Documentation | 2d | 9, 25
27 | Research implementations of AI Opponents | 4d | 13
28 | Research into the chosen AI technique | 7d | 27
29 | Develop a means to test the technique | 7d | 28
30 | Develop a Prototype of a 'Random' AI | 7d | 29
31 | Develop a Prototype AI using research & findings | 10d | 30
32 | (Cycle 5) User Stories / Task Cards | 3d | 27
33 | (Cycle 5) Coding | 5d | 13, 31, 32
34 | (Cycle 5) Testing & Documentation | 2d | 9, 33
35 | User Guide & Evaluation | 4d | 34

## PERT Analysis
Task | Days |  |  |  |  | Critical Path?
| Duration | Earliest Start | Earliest Finish | Latest Start | Latest Finish |  | Float Free Slack
Initial team meeting / Task allocations | 2d | 0 | 2 | 0 | 2 | Yes | -
Creation of Google Docs | 1d | 2 | 3 | 2 | 3 | Yes | -
Creation of Github Repo | 1d | 2 | 3 | 16 | 17 | No | 14 days
Non-functional requirements | 5d | 3 | 8 | 3 | 8 | Yes | -
Functional requirements | 4d | 3 | 7 | 4 | 8 | No | 1 day
Domain Requirements & Feasibility study | 5d | 8 | 13 | 8 | 13 | Yes | -
Risk Management | 4d | 8 | 12 | 9 | 13 | No | 1 day
Test Plan | 4d | 13 | 17 | 13 | 17 | Yes | -
Understanding C# | 10d | 3 | 13 | 17 | 27 | No | 14 days
Use Case | 4d | 17 | 21 | 19 | 23 | No | 2 days
Flowchart | 6d | 17 | 23 | 17 | 23 | Yes | -
Class Diagram | 4d | 23 | 27 | 23 | 27 | Yes | -
Graphics / Wireframes | 5d | 23 | 28 | 51 | 56 | No | 28 days
(Cycle 1) User Stories / Task Cards | 3d | 12 | 15 | 24 | 27 | No | 12 days
(Cycle 1) Coding | 8d | 27 | 35 | 27 | 35 | Yes | -
(Cycle 1) Testing & Documentation | 3d | 35 | 38 | 35 | 38 | Yes | -
(Cycle 2) User Stories / Task Cards | 2d | 38 | 40 | 38 | 40 | Yes | -
(Cycle 2) Coding | 4d | 40 | 44 | 40 | 44 | Yes | -
(Cycle 2) Testing & Documentation | 1d | 44 | 45 | 44 | 45 | Yes | -
(Cycle 3) User Stories / Task Cards | 2d | 45 | 47 | 45 | 47 | Yes | -
(Cycle 3) Coding | 5d | 47 | 52 | 47 | 52 | Yes | -
(Cycle 3) Testing & Documentation | 2d | 52 | 54 | 52 | 54 | Yes | -
(Cycle 4) User Stories / Task Cards | 2d | 54 | 56 | 54 | 56 | Yes | -
(Cycle 4) Coding | 5d | 56 | 61 | 56 | 61 | Yes | -
(Cycle 4) Testing & Documentation | 2d | 61 | 63 | 61 | 63 | Yes | -
Research implementations of AI Opponents | 4d | 27 | 31 | 31 | 35 | No | 4 days
Research into the chosen AI technique | 7d | 31 | 38 | 35 | 42 | No | 4 days
Develop a means to test the technique | 7d | 38 | 45 | 42 | 49 | No | 4 days
Develop a Prototype of a 'Random' AI | 7d | 45 | 52 | 49 | 56 | No | 4 days
Develop a Prototype AI using research & findings | 10d | 52 | 62 | 56 | 66 | No | 4 days
(Cycle 5) User Stories / Task Cards | 3d | 63 | 66 | 63 | 66 | Yes | -
(Cycle 5) Coding | 5d | 66 | 71 | 66 | 71 | Yes | -
(Cycle 5) Testing & Documentation | 2d | 71 | 73 | 71 | 73 | Yes | -
User Guide & Evaluation | 4d | 73 | 77 | 73 | 77 | Yes | -
77 Days / 57 Working Days

## Updated PERT Tasks & Timings
Task | Predicted |  |  |  |  | Actual
| Duration | Earliest Start | Earliest Finish | Latest Start | Latest Finish | Actual Start | Actual Finish | Member who completed | Additional Comments
Initial team meeting / Task allocations | 2d | 0 | 2 | 0 | 2 | 0 | 2 | Everyone | Took us a while to finally meet up, because people working a lot recently.
Creation of Google Docs | 1d | 2 | 3 | 2 | 3 | 2 | 3 | Mike
Creation of Github Repo | 1d | 2 | 3 | 16 | 17 | 2 | 3 | Jack
Non-functional requirements | 5d | 3 | 8 | 3 | 8 | 3 | 8 | Mike
Functional requirements | 4d | 3 | 7 | 4 | 8 | 3 | 8 | Mike | Took an extra Day, but no time lost.
Domain Requirements & Feasibility study | 5d | 8 | 13 | 8 | 13 | 8 | 14 | Mike | Took an extra day as was busy over the weekend.
Risk Management | 4d | 8 | 12 | 9 | 13 | 8 | 13 | Ellis | Other coursework lead to extra day, no time lost.
Test Plan | 4d | 13 | 17 | 13 | 17 | 14 | 18 | Ellis | Started late, as had to wait for all requirements
Understanding C# | 10d | 3 | 13 | 17 | 27 | 9 | 24 | Tom | Believes he has much better understanding now, even taking a few extra days
Use Case | 4d | 17 | 21 | 19 | 23 | 19 | 23 | Jack | Started a bit as was creating task cards.
Flowchart | 6d | 17 | 23 | 17 | 23 | 17 | 24 | Bayley | Took an extra day, as was planning out how the flowchart would run. Also had problems with dia, so moved midway to Lucidchart.
Class Diagram | 4d | 23 | 27 | 23 | 27 | 26 | 31 | Bayley | COVID-19 forced Bayley to return home for work, so had no computer. Done these by hand for now and sent them to the group chat.
Found it easier to make a sequence diagram first to help with class diagram. Sequence available in the documentation Documentation folder.
Graphics / Wireframes | 5d | 23 | 28 | 51 | 56 | 32 | 37 | Jack | Waited for class diagram, but no time lost as lots of float free slack.
(Cycle 1) User Stories / Task Cards | 3d | 12 | 15 | 24 | 27 | 15 | 19 | Jack | Done early as was free.
(Cycle 1) Coding | 8d | 27 | 35 | 27 | 35 | 31 | 39 | Tom | Started as soon as class diagram done.
(Cycle 1) Testing & Documentation | 3d | 35 | 38 | 35 | 38 | 40 | 44 | Tom / Ellis | Tom - Unit Tests, Ellis - Testing
(Cycle 2) User Stories / Task Cards | 2d | 38 | 40 | 38 | 40 | 44 | 46 | Jack
(Cycle 2) Coding | 4d | 40 | 44 | 40 | 44 | 46 | 51 | Tom | Took an extra day to ensure everything worked before testing.
(Cycle 2) Testing & Documentation | 1d | 44 | 45 | 44 | 45 | 51 | 54 | Tom / Ellis | Testing took longer, because both were at work.
(Cycle 3) User Stories / Task Cards | 2d | 45 | 47 | 45 | 47 | 55 | 58 | Jack
(Cycle 3) Coding | 5d | 47 | 52 | 47 | 52 | 58 | 66 | Tom | Trouble reading from a file, so had to input manually. Heavily undestimated cycle.
(Cycle 3) Testing & Documentation | 2d | 52 | 54 | 52 | 54 | 65 | 68 | Tom/Ellis | Testing orginally showed flaws, so went back to contiue coding.
(Cycle 4) User Stories / Task Cards | 2d | 54 | 56 | 54 | 56 | 68 | 69 | Jack
(Cycle 4) Coding | 5d | 56 | 61 | 56 | 61 | 69 | 79 | Tom | GUI provided some issues, especially displaying imaging. Passing variables between windows also provided to be a struggle.
(Cycle 4) Testing & Documentation | 2d | 61 | 63 | 61 | 63 | 80 | 81 | Tom / Ellis
Research implementations of AI Opponents | 4d | 27 | 31 | 31 | 35 | 39 | 48 | Bayley | Research done all on phone, took slightly longer. Will be written up when gets computer.
Research into the chosen AI technique | 7d | 31 | 38 | 35 | 42 | 48 | 57 | Bayley | Was busy working over the weekend, but eventully got computer from Brighton, so can write up research.
Develop a means to test the technique | 7d | 38 | 45 | 42 | 49 | 57 | 68 | Bayley | Started late as writing up the previous research. Used an old A-Level project to help implement so was done in python.
Develop a Prototype of a 'Random' AI | 7d | 45 | 52 | 49 | 56 | 70 | 79 | Bayley | Took a while to build an independent prototype in Java.
Develop a Prototype AI using research & findings | 10d | 52 | 62 | 56 | 66 | 82 | In Progress | Bayley | Ran out of time, some coding was complete.
(Cycle 5) User Stories / Task Cards | 3d | 63 | 66 | 63 | 66 | 82 | 84
(Cycle 5) Coding | 5d | 66 | 71 | 66 | 71 | 84 | In Progress | Tom | Ran out of time, implemented trading partially
(Cycle 5) Testing & Documentation | 2d | 71 | 73 | 71 | 73 | - | - | Tom / Ellis | Tested trading only, no AI
User Guide & Evaluation | 4d | 73 | 77 | 73 | 77 | 84 | 87 | Mike | Done all sprints
Deadline Day = 80 days (8th may) from Start
|  |  |  | Updated in April | Extended Deadline Date - 87 (15th May)
|  |  |  | Things to Note: | Bayley, at home, had no computer / laptop between day 25 (March 14) and day 46 (April 3rd) & was also working extended shifts
Ellis still working as key worker
Mike & Tom working from home.