## Tasks in Gantt format
Task | Description | Duration (Working Days) | Predecessor(s)
1 | Initial team meeting / Task allocations | 2d | None
2 | Creation of Google Docs | 1d | 2
3 | Creation of Github Repo | 1d | 2
4 | Non-functional requirements | 5d | 3
5 | Functional requirements | 4d | 3
6 | Domain Requirements & Feasibility study | 5d | 5,6
7 | Risk Management | 4d | 5,6
8 | Test Plan | 4d | 8
9 | Understanding C# | 10d | 4
10 | Use Case | 4d | 8
11 | Flowchart | 6d | 8
12 | Class Diagram | 4d | 11, 12
14 | Graphics / Wireframes | 5d | 11, 12
15 | (Cycle 1) User Stories / Task Cards | 3d | 8
16 | (Cycle 1) Coding | 8d | 10, 13, 15
17 | (Cycle 1) Testing & Documentation | 3d | 9, 18
18 | (Cycle 2) User Stories / Task Cards | 2d | 17
19 | (Cycle 2) Coding | 4d | 13, 18
20 | (Cycle 2) Testing & Documentation | 1d | 9, 19
21 | (Cycle 3) User Stories / Task Cards | 2d | 20
22 | (Cycle 3) Coding | 5d | 13, 21
23 | (Cycle 3) Testing & Documentation | 2d | 9, 22
24 | (Cycle 4) User Stories / Task Cards | 2d | 24
25 | (Cycle 4) Coding | 5d | 13, 14, 24
26 | (Cycle 4) Testing & Documentation | 2d | 9, 25
27 | Research implementations of AI Opponents | 4d | 13
28 | Research into the chosen AI technique | 7d | 27
29 | Develop a means to test the technique | 7d | 28
30 | Develop a Prototype of a 'Random' AI | 7d | 29
31 | Develop a Prototype AI using research & findings | 10d | 30
32 | (Cycle 5) User Stories / Task Cards | 3d | 27
33 | (Cycle 5) Coding | 5d | 13, 31, 32
34 | (Cycle 5) Testing & Documentation | 2d | 9, 33
35 | User Guide & Evaluation | 4d | 34

## PERT Analysis
Task | Days |  |  |  |  | Critical Path?
| Duration | Earliest Start | Earliest Finish | Latest Start | Latest Finish
Initial team meeting / Task allocations | 2d | 0 | 2 | 0 | 2 | Yes
Creation of Google Docs | 1d | 2 | 3 | 2 | 3 | Yes
Creation of Github Repo | 1d | 2 | 3 | 16 | 17 | No
Non-functional requirements | 5d | 3 | 8 | 3 | 8 | Yes
Functional requirements | 4d | 3 | 7 | 4 | 8 | No
Domain Requirements & Feasibility study | 5d | 8 | 13 | 8 | 13 | Yes
Risk Management | 4d | 8 | 12 | 9 | 13 | No
Test Plan | 4d | 13 | 17 | 13 | 17 | Yes
Understanding C# | 10d | 3 | 13 | 17 | 27 | No
Use Case | 4d | 17 | 21 | 19 | 23 | No
Flowchart | 6d | 17 | 23 | 17 | 23 | Yes
Class Diagram | 4d | 23 | 27 | 23 | 27 | Yes
Graphics / Wireframes | 5d | 23 | 28 | 51 | 56 | No
(Cycle 1) User Stories / Task Cards | 3d | 12 | 15 | 24 | 27 | No
(Cycle 1) Coding | 8d | 27 | 35 | 27 | 35 | Yes
(Cycle 1) Testing & Documentation | 3d | 35 | 38 | 35 | 38 | Yes
(Cycle 2) User Stories / Task Cards | 2d | 38 | 40 | 38 | 40 | Yes
(Cycle 2) Coding | 4d | 40 | 44 | 40 | 44 | Yes
(Cycle 2) Testing & Documentation | 1d | 44 | 45 | 44 | 45 | Yes
(Cycle 3) User Stories / Task Cards | 2d | 45 | 47 | 45 | 47 | Yes
(Cycle 3) Coding | 5d | 47 | 52 | 47 | 52 | Yes
(Cycle 3) Testing & Documentation | 2d | 52 | 54 | 52 | 54 | Yes
(Cycle 4) User Stories / Task Cards | 2d | 54 | 56 | 54 | 56 | Yes
(Cycle 4) Coding | 5d | 56 | 61 | 56 | 61 | Yes
(Cycle 4) Testing & Documentation | 2d | 61 | 63 | 61 | 63 | Yes
Research implementations of AI Opponents | 4d | 27 | 31 | 31 | 35 | No
Research into the chosen AI technique | 7d | 31 | 38 | 35 | 42 | No
Develop a means to test the technique | 7d | 38 | 45 | 42 | 49 | No
Develop a Prototype of a 'Random' AI | 7d | 45 | 52 | 49 | 56 | No
Develop a Prototype AI using research & findings | 10d | 52 | 62 | 56 | 66 | No
(Cycle 5) User Stories / Task Cards | 3d | 63 | 66 | 63 | 66 | Yes
(Cycle 5) Coding | 5d | 66 | 71 | 66 | 71 | Yes
(Cycle 5) Testing & Documentation | 2d | 71 | 73 | 71 | 73 | Yes
User Guide & Evaluation | 4d | 73 | 77 | 73 | 77 | Yes